## Summary
Note #1: Ячейки выделенные желтым цветом рассчитываются автоматически
Note #2: Данные должны указываться только за отчетный период (в примечаниях следует указывать, если данные за отчетный период отличаются от обычных)
Note #3. Примечание 3: Все время должно указываться в часах
Project name: |  | Linkavie
Project Manager: |  | Jane, Minakova
Date of report creation: |  | 2013-12-27
Report period: |  | 26.11.2013 – 27.12.2013
Number of working days: |  | 24
Can you characterize current Project state as completely successful? |  | No | If your answer is different from "Yes, of course", please fill in the sheet named "Potential Threats" in this document. If you think there are any additional threats that are not listed in the current set, please update the list with appropriate changes.
Table 1 - Important Project Events
Stage | Dates
Этап | According to the Current Plan | Actual Date | According to the Agreement
Project Start | 2013-11-26 | 2013-11-26 | 2013-11-26
Milestone #1 | 2013-12-23 | 2013-12-23 | 2013-12-20
Milestone #2 | 2014-01-15 |  | 2014-01-13
Milestone #3 | 2013-01-03 |  | 2014-01-30
Deadline | 2013-02-13 |  | 2014-02-11
Table 2
Project Role | Name | Time logging |  |  |  | Logged Time of Main Activities (in Redmine) |  | Notes (optional)
|  | Time spent (roughly), hrs per day | Workload (daily / on demand / number of hrs) | Time spent for main activities (development / design / testing / management) | The time spent for education, hrs | Main activities | Education
Project Manager | Jane, Minakova | 2 | every day | 50 |  | 0 | 0
Designer | Anton, Podorozhko | NA | on demand | 23 |  | 23 | 0
Software Engineer | Artem, Paliy | 8 | every day | 200 |  | 79.9 | 0
Software Engineer | Mikhail, Korovkin | 3.5 | 3.5 | 84.5 |  | 96.5 | 0
Software Engineer | Stanislav, Termosa | 8 | every day | 200 |  | 69.51 | 0
QA Engineer | Andrew, Najdenov | 8 | every day | 200 |  | 53.05 | 0
321.96
Table 3
Activity | Estimated time, hrs | Additional time (after Change request), hrs | Preapproved Time (Estimated time + Additional time), hrs | Actually spent time, hrs
Management | 44 | 0 | 44 | 50
Design | 34 | 0 | 34 | 23
Development | 246 | 32 | 278 | 484.5
QA | 24 | 0 | 24 | 200
Education | 0 | 0 | 0 | 0
Total | 348 | 32 | 380 | 757.5

## Activities
Date | Member | Activity | Project | Version | Issue | Issue Subject | Comment | Hours
2013-11-27 | Andrew Najdenov | Design | Linkavie |  | Task #63 | Test plan | Jane, here the TP | 5
2013-12-25 | Andrew Najdenov | Development | Linkavie |  | Bug #123 | Incorrect 'Discover Linkavie' arrow in IE. |  | 0.5
2013-12-23 | Andrew Najdenov | Development | Linkavie |  | Bug #124 | The list markers in IE are seen |  | 0.25
2013-12-26 | Andrew Najdenov | Testing | Linkavie |  | Bug #137 | Site content is shown without authorization on the test server. |  | 0.1
2013-12-23 | Andrew Najdenov | Development | Linkavie |  | Bug #164 | Orange frame inside textboxes are shown |  | 0.25
2013-12-23 | Andrew Najdenov | Development | Linkavie | Landing and Dashboard 0.1 | Task #235 | Friends invitation (back end) |  | 0.25
2013-12-23 | Andrew Najdenov | Development | Linkavie | Landing and Dashboard 0.1 | Task #257 | Invitation email |  | 1
2013-12-20 | Andrew Najdenov | Development | Linkavie | Landing and Dashboard 0.1 | Task #259 | Notification after invitation accept |  | 0.25
2013-12-23 | Andrew Najdenov | Development | Linkavie | Landing and Dashboard 0.1 | Task #259 | Notification after invitation accept |  | 0.5
2013-12-26 | Andrew Najdenov | Testing | Linkavie |  | Bug #263 | Contacts and invitation. Incorrect frame in FF browser. |  | 0.25
2013-12-25 | Andrew Najdenov | Development | Linkavie | Landing and Dashboard 0.1 | Bug #269 | Cancel at avatar uploading |  | 0.5
2013-12-26 | Andrew Najdenov | Testing | Linkavie |  | Bug #277 | 'Remember Me' feature does not work on IE. |  | 0.4
2013-12-26 | Andrew Najdenov | Testing | Linkavie | Landing and Dashboard 0.1 | Task #284 | Don't allow my contact page for not confirmed user |  | 0.1
2013-12-23 | Andrew Najdenov | Development | Linkavie | Landing and Dashboard 0.1 | Task #285 | Notification about restricted access |  | 0.25
2013-12-25 | Andrew Najdenov | Development | Linkavie | Landing and Dashboard 0.1 | Task #285 | Notification about restricted access |  | 0.1
2013-12-26 | Andrew Najdenov | Testing | Linkavie | Landing and Dashboard 0.1 | Task #297 | Possibility to send invitation to myself |  | 0.5
2013-12-26 | Andrew Najdenov | Testing | Linkavie |  | Bug #299 | Incorrect redirect after navigation from invitation link. |  | 1
2013-12-23 | Andrew Najdenov | Development | Linkavie |  | Bug #300 | Please fix error messages on Landing page and during password restoration. |  | 0.5
2013-12-25 | Andrew Najdenov | Development | Linkavie | Landing and Dashboard 0.1 | Task #301 | My Account.The application was frozen during the attempt of download the picture with height or width less that 168 pixels. |  | 0.5
2013-12-26 | Andrew Najdenov | Development | Linkavie | Landing and Dashboard 0.1 | Task #304 | Validation of invitation for NON-LINKAVIE user |  | 0.25
2013-12-25 | Andrew Najdenov | Development | Linkavie | Landing and Dashboard 0.1 | Task #341 | MIlestone Landing and Dashboard 0.1 testing |  | 18
2013-12-25 | Andrew Najdenov | Development | Linkavie | Landing and Dashboard 0.1 | Task #341 | MIlestone Landing and Dashboard 0.1 testing |  | 6
2013-12-27 | Andrew Najdenov | Testing | Linkavie | Landing and Dashboard 0.1 | Task #341 | MIlestone Landing and Dashboard 0.1 testing |  | 4
2013-12-27 | Andrew Najdenov | Testing | Linkavie | Landing and Dashboard 0.1 | Task #341 | MIlestone Landing and Dashboard 0.1 testing | Case regression (FF+ W7) and case updating. | 8
2013-12-25 | Andrew Najdenov | Development | Linkavie |  | Bug #348 | The first sign up message does not send. |  | 1
2013-12-25 | Andrew Najdenov | Development | Linkavie | Landing and Dashboard 0.1 | Task #350 | Excess users are present in the contact list of newly created user. |  | 1
2013-12-25 | Andrew Najdenov | Development | Linkavie | Landing and Dashboard 0.1 | Task #355 | Please add the sending of invitation from link at right top menu. |  | 0.5
2013-12-26 | Andrew Najdenov | Development | Linkavie | Landing and Dashboard 0.1 | Task #355 | Please add the sending of invitation from link at right top menu. |  | 0.25
2013-12-26 | Andrew Najdenov | Development | Linkavie | Landing and Dashboard 0.1 | Task #355 | Please add the sending of invitation from link at right top menu. |  | 0.1
2013-12-25 | Andrew Najdenov | Development | Linkavie | Landing and Dashboard 0.1 | Task #363 | The left side menu is pierced by top menu during the process of the site resizing. |  | 0.25
2013-12-26 | Andrew Najdenov | Development | Linkavie | Landing and Dashboard 0.1 | Task #366 | 'My account'. Change picture. If user is logged off then after pressing 'Upload' button should be redirected to the Landing page. |  | 0.5
2013-12-26 | Andrew Najdenov | Testing | Linkavie | Landing and Dashboard 0.1 | Task #366 | 'My account'. Change picture. If user is logged off then after pressing 'Upload' button should be redirected to the Landing page. |  | 0.25
2013-12-26 | Andrew Najdenov | Testing | Linkavie | Landing and Dashboard 0.1 | Task #366 | 'My account'. Change picture. If user is logged off then after pressing 'Upload' button should be redirected to the Landing page. |  | 0.1
2013-12-26 | Andrew Najdenov | Testing | Linkavie | Landing and Dashboard 0.1 | Task #370 | Default "my contacts" page |  | 0.4
2013-12-26 | Andrew Najdenov | Testing | Linkavie | Landing and Dashboard 0.1 | Task #374 | Change the text of notifications at blocked "my contacts" page |  | 0.25
2013-11-26 | Anton Podorozhko | Design | Linkavie | Landing and Dashboard 0.1 | Task #60 | Review all designs |  | 4
2013-11-29 | Anton Podorozhko | Design | Linkavie | Landing and Dashboard 0.1 | Task #60 | Review all designs |  | 5
2013-12-09 | Anton Podorozhko | Design | Linkavie | Landing and Dashboard 0.1 | Task #60 | Review all designs |  | 4
2013-12-12 | Anton Podorozhko | Design | Linkavie | Landing and Dashboard 0.1 | Task #60 | Review all designs |  | 4
2013-12-10 | Anton Podorozhko | Design | Linkavie | Landing and Dashboard 0.1 | Task #172 | New design of fields and buttons |  | 4
2013-12-19 | Anton Podorozhko | Design | Linkavie | Landing and Dashboard 0.1 | Task #237 | Validation of an invitation (design) |  | 2
2013-12-03 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #78 | Registration |  | 3
2013-12-04 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #80 | Forgot password |  | 3
2013-12-23 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Feature #89 | Dashboard page |  | 1
2013-12-05 | Artem Paliy | Development | Linkavie |  | Bug #98 | E-mail not validated at all in the Forgot password page. |  | 1
2013-12-04 | Artem Paliy | Development | Linkavie |  | Task #122 | Page restore password |  | 0.5
2013-12-23 | Artem Paliy | Development | Linkavie |  | Task #122 | Page restore password |  | 2
2013-12-23 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #125 | Account confirmation |  | 2
2013-12-05 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Feature #130 | My profile page |  | 0.5
2013-12-23 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Feature #130 | My profile page |  | 2
2013-12-23 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #135 | Add the popup when user is not confirmed |  | 2
2013-12-23 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #165 | Right top menu |  | 1
2013-12-10 | Artem Paliy | Development | Linkavie |  | Bug #166 | Registration page. The message for e-mail which already in use are not clear. |  | 0.1
2013-12-23 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #188 | Resend email process |  | 2
2013-12-23 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #189 | Confirmation email |  | 0.5
2013-12-23 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #213 | Delete user after 5 days without confirmation |  | 2
2013-12-23 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #225 | Add notification after password changing |  | 1
2013-12-23 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #231 | Default avatar |  | 0.5
2013-12-23 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #235 | Friends invitation (back end) |  | 10
2013-12-23 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #239 | Stay checked 'remember me' |  | 4
2013-12-23 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #240 | Validation of an invitation (back end) |  | 5
2013-12-23 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #257 | Invitation email |  | 1
2013-12-23 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #258 | Validation of an invitation (front end) |  | 6
2013-12-23 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #259 | Notification after invitation accept |  | 1
2013-12-25 | Artem Paliy | Development | Linkavie | Multimedia Vault 0.2 | Task #273 | Vault architecture |  | 3
2013-12-25 | Artem Paliy | Development | Linkavie | Multimedia Vault 0.2 | Task #273 | Vault architecture |  | 1
2013-12-26 | Artem Paliy | Development | Linkavie | Multimedia Vault 0.2 | Task #273 | Vault architecture |  | 2
2013-12-23 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #283 | Show new friend at "my contact" page |  | 4
2013-12-24 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #284 | Don't allow my contact page for not confirmed user |  | 0.5
2013-12-24 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #297 | Possibility to send invitation to myself |  | 0.5
2013-12-27 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #297 | Possibility to send invitation to myself |  | 0.5
2013-12-24 | Artem Paliy | Development | Linkavie |  | Bug #299 | Incorrect redirect after navigation from invitation link. |  | 4
2013-12-23 | Artem Paliy | Development | Linkavie |  | Bug #300 | Please fix error messages on Landing page and during password restoration. |  | 0.3
2013-12-24 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #304 | Validation of invitation for NON-LINKAVIE user |  | 0.5
2013-12-24 | Artem Paliy | Development | Linkavie |  | Bug #348 | The first sign up message does not send. |  | 1
2013-12-24 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #350 | Excess users are present in the contact list of newly created user. |  | 1
2013-12-27 | Artem Paliy | Development | Linkavie | Multimedia Vault 0.2 | Task #364 | The Vault page |  | 4
2013-12-26 | Artem Paliy | Development | Linkavie | Multimedia Vault 0.2 | Task #368 | Add the pictures to the vault (backend) |  | 4
2013-12-27 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #388 | Send invitation for different emails |  | 1.5
2013-12-23 | Artem Paliy | Development | Linkavie | Landing and Dashboard 0.1 | Task #271 | Structure of folders in DB for avatars |  | 1
2013-11-28 | Mikhail Korovkin | Design | Linkavie | Landing and Dashboard 0.1 | Task #59 | Set up hosting and environment |  | 3
2013-11-29 | Mikhail Korovkin | Development | Linkavie | Landing and Dashboard 0.1 | Task #59 | Set up hosting and environment | setup alpha vhost, configure jenkins and create setup job | 5
2013-12-02 | Mikhail Korovkin | Development | Linkavie | Landing and Dashboard 0.1 | Task #59 | Set up hosting and environment |  | 6
2013-12-03 | Mikhail Korovkin | Development | Linkavie | Landing and Dashboard 0.1 | Task #59 | Set up hosting and environment |  | 3
2013-12-04 | Mikhail Korovkin | Development | Linkavie | Landing and Dashboard 0.1 | Task #59 | Set up hosting and environment |  | 5.5
2013-12-05 | Mikhail Korovkin | Development | Linkavie | Landing and Dashboard 0.1 | Task #59 | Set up hosting and environment |  | 1.5
2013-12-02 | Mikhail Korovkin | Development | Linkavie | Landing and Dashboard 0.1 | Task #61 | Database structure |  | 2
2013-12-05 | Mikhail Korovkin | Development | Linkavie | Landing and Dashboard 0.1 | Task #61 | Database structure |  | 2
2013-12-09 | Mikhail Korovkin | Development | Linkavie | Landing and Dashboard 0.1 | Task #61 | Database structure |  | 6
2013-12-10 | Mikhail Korovkin | Development | Linkavie | Landing and Dashboard 0.1 | Task #61 | Database structure |  | 6.5
2013-12-11 | Mikhail Korovkin | Development | Linkavie | Landing and Dashboard 0.1 | Task #61 | Database structure |  | 3
2013-12-12 | Mikhail Korovkin | Development | Linkavie | Landing and Dashboard 0.1 | Task #61 | Database structure |  | 2
2013-12-13 | Mikhail Korovkin | Development | Linkavie | Landing and Dashboard 0.1 | Task #61 | Database structure |  | 4
2013-12-16 | Mikhail Korovkin | Design | Linkavie | Landing and Dashboard 0.1 | Task #218 | Support and review |  | 8
2013-12-18 | Mikhail Korovkin | Development | Linkavie | Landing and Dashboard 0.1 | Task #218 | Support and review |  | 8
2013-12-20 | Mikhail Korovkin | Development | Linkavie | Landing and Dashboard 0.1 | Task #218 | Support and review |  | 4.5
2013-12-23 | Mikhail Korovkin | Development | Linkavie | Landing and Dashboard 0.1 | Task #218 | Support and review | server configuration, enabling swap for composer update, edit cron script | 5
2013-12-23 | Mikhail Korovkin | Development | Linkavie | Landing and Dashboard 0.1 | Task #218 | Support and review |  | 1.5
2013-12-24 | Mikhail Korovkin | Development | Linkavie | Landing and Dashboard 0.1 | Task #218 | Support and review |  | 8
2013-12-25 | Mikhail Korovkin | Development | Linkavie | Landing and Dashboard 0.1 | Task #218 | Support and review |  | 3
2013-12-26 | Mikhail Korovkin | Development | Linkavie | Landing and Dashboard 0.1 | Task #218 | Support and review |  | 5
2013-12-27 | Mikhail Korovkin | Development | Linkavie | Landing and Dashboard 0.1 | Task #218 | Support and review |  | 4
2013-11-27 | Stanislav Termosa | Development | Linkavie |  | Task #64 | Html design of landing page |  | 4
2013-11-27 | Stanislav Termosa | Development | Linkavie |  | Task #64 | Html design of landing page | Add styles for layout and forms. Should be done: styles for checkbox element and aligns for text | 4
2013-11-28 | Stanislav Termosa | Development | Linkavie |  | Task #64 | Html design of landing page | It's responsible and with pretty checkboxes | 0.5
2013-12-09 | Stanislav Termosa | Design | Linkavie |  | Task #64 | Html design of landing page | Did | 0.16
2013-12-12 | Stanislav Termosa | Design | Linkavie |  | Task #64 | Html design of landing page | Add call to action colors, fix filters, resize margins for popups, fix sliding on dashboard, hide footer on landing page, add script for notification hiding, refactoring for forms, change error displaying method, etc. | 5
2013-11-29 | Stanislav Termosa | Development | Linkavie |  | Task #79 | Registrarion page make up |  | 3
2013-12-12 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #80 | Forgot password | Add markup | 0.25
2013-12-17 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #80 | Forgot password | Done | 1
2013-12-17 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #80 | Forgot password | Done | 1
2013-12-06 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #90 | Dashboard page make up |  | 8
2013-12-09 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #90 | Dashboard page make up | Make interactive search | 0.5
2013-12-09 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #90 | Dashboard page make up | Add popup for user stats | 5
2013-12-10 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #90 | Dashboard page make up | Added popups and notifyes | 5
2013-12-04 | Stanislav Termosa | Design | Linkavie |  | Bug #101 | Border of the logo block on the header are visible in IE 11. | It will be fixed after less compilation (in production version) | 0.5
2013-12-11 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #105 | Add the left side menu to dashboard page | Menu is done | 1
2013-12-10 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #167 | Form for contact us | Markup is done | 0.16
2013-12-13 | Stanislav Termosa | Design | Linkavie |  | Bug #171 | It is no focus on blog area after clicking on the 'Discover Linkavie' link. |  | 0.1
2013-12-13 | Stanislav Termosa | Design | Linkavie |  | Bug #174 | Menu button not changed color from white to yellow. |  | 0.25
2013-12-13 | Stanislav Termosa | Design | Linkavie |  | Bug #177 | Width of textboxes 'Email' and 'Password' is not same as width of 'Login' button. | Should be fixed. Test it, please | 0
2013-12-13 | Stanislav Termosa | Design | Linkavie |  | Bug #178 | Placeholders 'Email' and 'Password' is cropped after landing page downloading. | I did form by other way. It must works correct now. Test it please | 0.4
2013-12-13 | Stanislav Termosa | Design | Linkavie |  | Bug #181 | Dashboard. Dropdown menu (Top right corner) dissapears during slow mouse pointer moving. | Fixed | 0.4
2013-12-20 | Stanislav Termosa | Design | Linkavie |  | Bug #181 | Dashboard. Dropdown menu (Top right corner) dissapears during slow mouse pointer moving. | IE is so especial! | 0.16
2013-12-12 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #185 | Modification of menu bar | Change style of bar and tooltips | 0.5
2013-12-13 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #185 | Modification of menu bar | Fix jumping | 0.5
2013-12-13 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #185 | Modification of menu bar | Hide content when wrapper is to low | 0.4
2013-12-13 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #193 | Add breadcrunmbs | Done | 0.5
2013-12-20 | Stanislav Termosa | Design | Linkavie |  | Bug #195 | There are no placeholders on Landing page, Registration page, Forgot password page and Restore password page. | IE is so especial! | 0.6
2013-12-16 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Feature #198 | Contact page | Add markup for contacts page | 3
2013-12-16 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #204 | Add the message at forgot password page | Add text line on forgot-password page | 0.4
2013-12-17 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #210 | My profile page html coding | markup profile page | 3
2013-12-16 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #224 | Change the text of password reset instruction email | Changed | 0.16
2013-12-19 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #236 | Friends invitation (front end) | Designed | 2.5
2013-12-27 | Stanislav Termosa | Design | Linkavie |  | Bug #265 | Incorrect working menus with arrow in logged in condition. | Replace moving by hiding content in slide menu | 0.33
2013-12-20 | Stanislav Termosa | Design | Linkavie |  | Bug #267 | My Contacts Page. Left side menu was slightly trimmed, | Fixed | 0.5
2013-12-25 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Bug #269 | Cancel at avatar uploading | Done | 0.5
2013-12-20 | Stanislav Termosa | Development | Linkavie | Landing and Dashboard 0.1 | Task #270 | Less to CSS | Local setting 'environment' define what kind of stylesheet be used | 1
2013-12-24 | Stanislav Termosa | Design | Linkavie | Multimedia Vault 0.2 | Task #276 | Vault folder view | Import custom scrollbar | 1.5
2013-12-25 | Stanislav Termosa | Design | Linkavie | Multimedia Vault 0.2 | Task #276 | Vault folder view | Markup vault page with folders list and thumbnails | 4
2013-12-26 | Stanislav Termosa | Design | Linkavie | Multimedia Vault 0.2 | Task #276 | Vault folder view | Menu is fixed | 0.5
2013-12-27 | Stanislav Termosa | Design | Linkavie | Multimedia Vault 0.2 | Task #276 | Vault folder view | Add tooltips without design | 0.6
2013-12-26 | Stanislav Termosa | Development | Linkavie |  | Bug #277 | 'Remember Me' feature does not work on IE. | Fix IE-placeholder extension | 0.6
2013-12-23 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #285 | Notification about restricted access | Denied access (frontend) | 0.16
2013-12-26 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #297 | Possibility to send invitation to myself | Trying to reproduce this problem | 0.16
2013-12-27 | Stanislav Termosa | Testing | Linkavie | Landing and Dashboard 0.1 | Task #297 | Possibility to send invitation to myself |  | 0.24
2013-12-25 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #355 | Please add the sending of invitation from link at right top menu. | Animate "Invite friends" link | 0.24
2013-12-25 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #355 | Please add the sending of invitation from link at right top menu. | Holly Ctrl + F5 | 0.04
2013-12-26 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #355 | Please add the sending of invitation from link at right top menu. | This problem fixed and by the way fixed black line on hover to size bar in user stats slide menu | 0.4
2013-12-25 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #363 | The left side menu is pierced by top menu during the process of the site resizing. | Fixed | 0.16
2013-12-25 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #366 | 'My account'. Change picture. If user is logged off then after pressing 'Upload' button should be redirected to the Landing page. | Check for errors at uploading pictures | 0.6
2013-12-26 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #366 | 'My account'. Change picture. If user is logged off then after pressing 'Upload' button should be redirected to the Landing page. | Add redirect | 0.16
2013-12-27 | Stanislav Termosa | Development | Linkavie | Multimedia Vault 0.2 | Task #367 | Add the pictures to the vault (frontend) | Include file API | 3.5
2013-12-26 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #370 | Default "my contacts" page | Added | 1.1
2013-12-26 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #371 | Changes at adding friends popup | Add notice, change text | 0.7
2013-12-26 | Stanislav Termosa | Development | Linkavie | Landing and Dashboard 0.1 | Task #371 | Changes at adding friends popup | Fixed | 0.1
2013-12-26 | Stanislav Termosa | Design | Linkavie | Landing and Dashboard 0.1 | Task #374 | Change the text of notifications at blocked "my contacts" page | Add notification and bind action to resend link | 0.24
2013-12-26 | Stanislav Termosa | Development | Linkavie |  | Bug #379 | No message about successful invitation if user which used invitation link is already logged in. | I have been identifying problem on client side | 0.24
321.96

## Potential Threats
Страница в стадии разработки
| Признаки | Важность фактора (ориентировочно) низкая / средняя / высокая
Не вкладываемся в сроки
Значительно превышаем согласованный Estimate
Люди недогружены
Люди недовольны общением с Заказчиком
Не хватает функций Redmine / Jira
Хочу улучшить процесс ….
Трудность коммуникации с Заказчиком
Несогласованность требований
Нет апрува на увеличение сроков в связи с запрошенным Change Request
Нехватка сотрудников на реализацию задач (увеличение трудозатрат)
Концентрация компетенций в одних руках (нет возможности распараллелить задачи в команде)
Быстрое согласование документации без замечаний, вопросов и уточнений со стороны лиц, принимающих решение
Длительный процесс согласования документов
Низкая скорость реакции на письма и запросы
Длительные обсуждения вопросов в процессе работы
Приоритетность текущей работы (каждая новая входящая задача важнее уже начатой)
Неконтролируемое появление новых требований в процессе работы без изменения границ дедлайнов
Дублирование информации
Появление критичных требований перед сдачей подсистемы / модуля / проекта
Уход специалиста
Несогласованность отпусков / выходных участников команды
Снижение качества продукта (метрики?)
Отсутствие необходимого оборудования для тестирования / разработки
Свой вариант