## Estimate
PRELIMINARY PROJECT ESTIMATE |  | #0139-001-001-EST
Keyword Analyzer Tool |  | 05-MAY-2014
PREPARED FOR: Jeremy Ferguson
PREPARED BY: Yevgeniya Minakova - Project Manager
REVIEWED BY: V. Casan
# | DESCRIPTION | OPTIMISTIC ESTIMATE, HRS | PESSIMISTIC ESTIMATE, HRS
1 | PRE-STUDY / PREPARING COMMITTABLE PLAN | 45 | 57
| Product vision development | 10 | 12
| Product requirements workshops | 5 | 7
| User experience concept design | 6 | 8
| Product requirements specification and approval | 9 | 11
| Project estimation and planning | 10 | 12
| Management and communication during pre-study | 5 | 7
2 | "ITERATION ZERO" | 30 | 42
| High-level architecture and system design | 4 | 6
| Test strategy planning | 8 | 10
| Graphics design | 8 | 10
| Development environment setup/ server setup, install zend skeleton | 4 | 6
| Testing environment setup | 2 | 4
| Staging environment setup | 4 | 6
3 | CONSTRUCTION | 84 | 119
| General layout | 6 | 8
| Home page with text and images | 4 | 6
| Login/log out/register/forgot password | 11 | 15
| Contact us with emailing | 3 | 4
| Static faq | 5 | 6
| My account | 6 | 7
| My account access logs | 2 | 3
| Donate button | 6 | 9
| Single keyword analysis with filter | 24 | 36
| Download keyword analysis in csv format | 4 | 6
| Store keyword | 5 | 7
| Show google trend of single keyword | 8 | 12
4 | STABILIZATION AND DELIVERY | 42 | 56
| Regression testing | 14 | 18
| User interface testing | 5 | 9
| Release stabilization | 20 | 23
| Deployment to staging environment | 1 | 2
| Deployment to production environment | 1 | 2
| Acceptance testing support | 1 | 2
5 | MANAGEMENT AND COMMUNICATION | 26 | 40
| Product requirements clarifications and updates | 8 | 10
| Iteration planning meetings | 4 | 6
| Iteration retrospective meetings | 4 | 6
| Daily progress & status meetings | 4 | 4
| Change management | 2 | 6
| Project management and communication | 4 | 8
| GRAND TOTAL | 227 | 314

## Lookups (hidden)
L | L_Min | L_Likely | L_Buffer | L_Max
M | M_Min | M_Likely | M_Buffer | M_Max
S | S_Min | S_Likely | S_Buffer | S_Max | S | P | Yes | 90%
XL | XL_Min | XL_Likely | XL_Buffer | XL_Max | D | S | No | 99%
XS | XS_Min | XS_Likely | XS_Buffer | XS_Max | B | D | N/A
XXL | XXL_Min | XXL_Likely | XXL_Buffer | XXL_Max | T | B
XXS | XXS_Min | XXS_Likely | XXS_Buffer | XXS_Max |  | T
I
| R | D | C | T | M | M
1 | 0.04 | 0.1 | 0.61 | 0.16 | 0.09 |  | Test data creation
5 | 0.04 | 0.124 | 0.528 | 0.199 | 0.109
25 | 0.04 | 0.14 | 0.49 | 0.23 | 0.1
75 | 0.055 | 0.145 | 0.465 | 0.23 | 0.105
125 | 0.07 | 0.15 | 0.44 | 0.23 | 0.11
300 | 0.075 | 0.15 | 0.395 | 0.26 | 0.12
500 | 0.08 | 0.15 | 0.35 | 0.29 | 0.13
| R | D | C | T | M
Business Systems | -0.03 | -0.07 | 0.05 | -0.07 | 0.03
Device Drivers | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Embedded Systems | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Engineering Systems | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Internal Intranet Systems | -0.03 | -0.07 | 0.05 | -0.07 | 0.03
Public Internet Systems | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Scientific Systems | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Shrink-Wrap | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Systems Software | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Telecommunications | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Advanced multi-site surveys application (MLR) | 300 | Internal Intranet Systems
Automated document archival solution (LTA) | 125 | Business Systems
Complex SharePoint-based public CMS solution (MTT) | 125 | Public Internet Systems
Highly customizable BI solution with interactive GUI (ACE) | 500 | Business Systems
Interactive iPad brochures for automotive industry (Subaru) | 25 | Shrink-Wrap
Racing event support website (WMRT) | 25 | Public Internet Systems
Simple data/format conversion solution (FSR) | 25 | Business Systems
Sophisticated data conversion/mapping solution (O2O) | 75 | Business Systems
Sophisticated enterprise content management platform (PLD) | 500 | Business Systems
Trivia game rich Internet application (VRG) | 5 | Public Internet Systems
Trivia game server-side application (VRG) | 5 | Public Internet Systems
Web portal integrated with internal business system (PWP) | 25 | Public Internet Systems
Add new project size and classification entries above this line