## Estimate
PRELIMINARY PROJECT ESTIMATE |  | #0146 -001-001-EST
26-MAY-2014
PREPARED FOR:
PREPARED BY:
REVIEWED BY:
# | DESCRIPTION | OPTIMISTIC ESTIMATE, HRS | PESSIMISTIC ESTIMATE, HRS
1 | PRE-STUDY / PREPARING COMMITTABLE PLAN | 6 | 0
| Product vision development | 1
Product requirements workshops
User experience concept design
| Product requirements specification and approval | 2
| Project estimation and planning | 3
Management and communication during pre-study
2 | "ITERATION ZERO" | 0 | 0
High-level architecture and system design
Test strategy planning
Graphics design
Development environment setup/ server setup, install zend skeleton
Testing environment setup
Staging environment setup
3 | CONSTRUCTION | 127 | 262
| Specify functionality and avialable user action | 5 | 16
| General layout (layout, header, menu, sub-menu, account info, dropdowns with links) | 8 | 15
| Store - File Explorer (tree file list, menus, dialogs) | 12 | 18
| Store - File Sync Status | 5 | 8
| Store - Library (with 5 sub pages, no mockups/description present, with CRUD actions and search) | 40 | 80
| Process - Task Status (with subpages, no mockups/description present) | 12 | 24
| Process - Task Exprorer | 8 | 12
| Analyze - Analitics (with subpages, no mockups/description present) | 12 | 15
| Analyze - 4 other subpages (no mockups/description present) | 24 | 60
| Exchange - no mockups/description provided | 6 | 30
4 | STABILIZATION AND DELIVERY | 0 | 0
Regression testing
User interface testing
Release stabilization
Deployment to staging environment
Deployment to production environment
Acceptance testing support
5 | MANAGEMENT AND COMMUNICATION | 0 | 0
Product requirements clarifications and updates
Iteration planning meetings
Iteration retrospective meetings
Daily progress & status meetings
Change management
Project management and communication
| GRAND TOTAL | 138 | 278

## Lookups (hidden)
L | L_Min | L_Likely | L_Buffer | L_Max
M | M_Min | M_Likely | M_Buffer | M_Max
S | S_Min | S_Likely | S_Buffer | S_Max | S | P | Yes | 90%
XL | XL_Min | XL_Likely | XL_Buffer | XL_Max | D | S | No | 99%
XS | XS_Min | XS_Likely | XS_Buffer | XS_Max | B | D | N/A
XXL | XXL_Min | XXL_Likely | XXL_Buffer | XXL_Max | T | B
XXS | XXS_Min | XXS_Likely | XXS_Buffer | XXS_Max |  | T
I
| R | D | C | T | M | M
1 | 0.04 | 0.1 | 0.61 | 0.16 | 0.09 |  | Test data creation
5 | 0.04 | 0.124 | 0.528 | 0.199 | 0.109
25 | 0.04 | 0.14 | 0.49 | 0.23 | 0.1
75 | 0.055 | 0.145 | 0.465 | 0.23 | 0.105
125 | 0.07 | 0.15 | 0.44 | 0.23 | 0.11
300 | 0.075 | 0.15 | 0.395 | 0.26 | 0.12
500 | 0.08 | 0.15 | 0.35 | 0.29 | 0.13
| R | D | C | T | M
Business Systems | -0.03 | -0.07 | 0.05 | -0.07 | 0.03
Device Drivers | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Embedded Systems | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Engineering Systems | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Internal Intranet Systems | -0.03 | -0.07 | 0.05 | -0.07 | 0.03
Public Internet Systems | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Scientific Systems | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Shrink-Wrap | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Systems Software | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Telecommunications | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Advanced multi-site surveys application (MLR) | 300 | Internal Intranet Systems
Automated document archival solution (LTA) | 125 | Business Systems
Complex SharePoint-based public CMS solution (MTT) | 125 | Public Internet Systems
Highly customizable BI solution with interactive GUI (ACE) | 500 | Business Systems
Interactive iPad brochures for automotive industry (Subaru) | 25 | Shrink-Wrap
Racing event support website (WMRT) | 25 | Public Internet Systems
Simple data/format conversion solution (FSR) | 25 | Business Systems
Sophisticated data conversion/mapping solution (O2O) | 75 | Business Systems
Sophisticated enterprise content management platform (PLD) | 500 | Business Systems
Trivia game rich Internet application (VRG) | 5 | Public Internet Systems
Trivia game server-side application (VRG) | 5 | Public Internet Systems
Web portal integrated with internal business system (PWP) | 25 | Public Internet Systems
Add new project size and classification entries above this line