## Estimate
PRELIMINARY PROJECT ESTIMATE |  | #0152-001-001-EST
Ecommerce multistore |  | 04-JUN-2014 |  | НЕ ЗАБЫТЬ УДАЛИТЬ ЯЧЕЙКИ ВЫДЕЛЕННЫЕ ЖЕЛТЫМ ЦВЕТОМ!!!!
PREPARED BY: Anna Khodyrevska - Project Manager
REVIEWED BY: Anatoly Lenshin - Program Director
|  | Provided by Developes |  | BUFFER, HRS |  | TO CLIENT
# | DESCRIPTION | OPTIMISTIC ESTIMATE, HRS | PESSIMISTIC ESTIMATE, HRS | FOR OPTIMISTIC, HRS | FOR PESSIMISTIC, HRS | OPTIMISTIC ESTIMATE, HRS | PESSIMISTIC ESTIMATE, HRS | ASSUMPTIONS
0 | "ITERATION ZERO" | 4 | 6 | 0 | 2 | 4 | 8
| Development environment setup | 4 | 6 | 0 | 2 | 4 | 8
1 | CONSTRUCTION | 112 | 190 | 20 | 38 | 132 | 228
Redesign / Creating mockups:
| Mockup of the Main Page | 18 | 36 | 2 | 4 | 20 | 40 | Estimation provided according to the following assumptions: - one site instance only, meaning the same design for both requested sites; - all required graphics provided by customer; - mobile responsive design.
| Mockup for categories | 12 | 20 | 2 | 4 | 14 | 24
| Mockup for the page with goods/services | 8 | 16 | 2 | 4 | 10 | 20
| Mockup for Shopping Cart | 10 | 18 | 2 | 4 | 12 | 22
| Mockup for posts | 10 | 18 | 2 | 4 | 12 | 22
| Calendar development: |  |  |  |  | 0 | 0
| Development of booking enhancement Creating basic logic for events management Creating tables | 10 | 16 | 2 | 4 | 12 | 20 | The scope of features for the service https://www.mindbodyonline.com/full-feature-list is rather significant. Please specify the exact scope of required functionality, the list of reports and statistics that should be generated be the system. By default booking service is not implemented in Magento, which means we have to add this enhancement in scope od development activities. Estimation given according to the following assumption: - development of minimal functionality scope, mentioned on the screenshots, provided by customer.
| Development of Administration section - lessons management - events management - teachers/trainers management - students management - rooms management - reports and statistics | 25 | 36 | 4 | 6 | 29 | 42
| Frontend development - displaying lessons schedule - displaying filters | 15 | 24 | 4 | 6 | 19 | 30
| Setup and configure project in live | 4 | 6 | 0 | 2 | 4 | 8
2 | STABILIZATION AND DELIVERY | 152 | 234 | 12 | 28 | 164 | 262
| Functional testing | 38 | 60 | 4 | 8 | 42 | 68
| Code stabilization | 40 | 56 | 2 | 4 | 42 | 60
| Regression testing | 28 | 58 | 0 | 4 | 28 | 62
| Smoke testing before release | 8 | 12 | 2 | 4 | 10 | 16
| Sanity testing on live environment | 38 | 48 | 4 | 8 | 42 | 56
3 | MANAGEMENT AND COMMUNICATION | 86 | 102 | 3 | 16 | 153 | 118
| Product requirements clarifications and updates | 10 | 12 | 2 | 4 | 10 | 16
| Progress & status meetings | 6 | 10 | 0 | 4 | 42 | 14
| Change management | 6 | 8 | 1 | 2 | 89 | 10
| Project management and communication | 64 | 72 | 0 | 6 | 12 | 78
| GRAND TOTAL | 354 | 532 | 35 | 84 | 453 | 616

## Lookups (hidden)
L | L_Min | L_Likely | L_Buffer | L_Max
M | M_Min | M_Likely | M_Buffer | M_Max
S | S_Min | S_Likely | S_Buffer | S_Max | S | P | Yes | 90%
XL | XL_Min | XL_Likely | XL_Buffer | XL_Max | D | S | No | 99%
XS | XS_Min | XS_Likely | XS_Buffer | XS_Max | B | D | N/A
XXL | XXL_Min | XXL_Likely | XXL_Buffer | XXL_Max | T | B
XXS | XXS_Min | XXS_Likely | XXS_Buffer | XXS_Max |  | T
I
| R | D | C | T | M | M
1 | 0.04 | 0.1 | 0.61 | 0.16 | 0.09 |  | Test data creation
5 | 0.04 | 0.124 | 0.528 | 0.199 | 0.109
25 | 0.04 | 0.14 | 0.49 | 0.23 | 0.1
75 | 0.055 | 0.145 | 0.465 | 0.23 | 0.105
125 | 0.07 | 0.15 | 0.44 | 0.23 | 0.11
300 | 0.075 | 0.15 | 0.395 | 0.26 | 0.12
500 | 0.08 | 0.15 | 0.35 | 0.29 | 0.13
| R | D | C | T | M
Business Systems | -0.03 | -0.07 | 0.05 | -0.07 | 0.03
Device Drivers | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Embedded Systems | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Engineering Systems | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Internal Intranet Systems | -0.03 | -0.07 | 0.05 | -0.07 | 0.03
Public Internet Systems | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Scientific Systems | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Shrink-Wrap | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Systems Software | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Telecommunications | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Advanced multi-site surveys application (MLR) | 300 | Internal Intranet Systems
Automated document archival solution (LTA) | 125 | Business Systems
Complex SharePoint-based public CMS solution (MTT) | 125 | Public Internet Systems
Highly customizable BI solution with interactive GUI (ACE) | 500 | Business Systems
Interactive iPad brochures for automotive industry (Subaru) | 25 | Shrink-Wrap
Racing event support website (WMRT) | 25 | Public Internet Systems
Simple data/format conversion solution (FSR) | 25 | Business Systems
Sophisticated data conversion/mapping solution (O2O) | 75 | Business Systems
Sophisticated enterprise content management platform (PLD) | 500 | Business Systems
Trivia game rich Internet application (VRG) | 5 | Public Internet Systems
Trivia game server-side application (VRG) | 5 | Public Internet Systems
Web portal integrated with internal business system (PWP) | 25 | Public Internet Systems
Add new project size and classification entries above this line