## Sheet1
# | Task/Bug | Title | Description/Steps | Severity | Status | Comment
1 | T | Login with Event Id | Screen and function | Blocker | Disappeared | QR code, event id f-ty can't be verified
5 | B | Camera crashes on clicking take photo btn |  | Blocker | Re-opened | Picture could not be made, test data is not producable
36 | T | Taking picture. Preview screen |  | Blocker | Can't be verified | Has blocker bug
4 | T | Camera. Taking picture |  | Blocker | Can't be verified | Application galleries view, Photo view, Photo edit can't be verified. See #5
21 | B | Gallery. Delete photo - on confirmation app crashes. |  | Blocker | New
35 | T | Camera. Landscape. |  | Critical | Not implemented
7 | T | Terms and Conds page |  | Critical | Not implemented
8 | T | 2 languages support |  | Critical | Not implemented
14 | T | Server folder selector |  | Critical | Not implemented
15 | T | Use only WiFi option |  | Critical | Not implemented
17 | T | Log out |  | Critical | Not implemented
19 | T | FB sharing |  | Critical | Not implemented
25 | T | Photo view. Zoom/unzoom by double tap or pinch, max 4x |  | Critical | Not implemented
26 | T | Photo view. Landscape |  | Critical | Not implemented
30 | T | Supporting of different screens |  | Critical | Not implemented
31 | T | Supporting Android 4.2+ |  | Critical | Not implemented
37 | T | Ready API methods interaction |  | Critical | Not implemented
13 | T | Settings |  | Critical | Incomplete | Same option names, not working controls, doesn't correspond to design
2 | T | Login with QR code |  | Critical | Can't be verified | See #1
3 | T | Accept Terms and Cond checkbox |  | Critical | Can't be verified | Login screen is missing. See #1
9 | T | Application gallery view |  | Critical | Can't be verified | Test data is not producable. See #5
11 | T | Server Galleries view |  | Critical | Can't be verified | Test data is not producable. See #5
16 | T | Add/skip instant description |  | Critical | Can't be verified | See #5, 36
18 | T | Galleries. Edit mode |  | Critical | Can't be verified | Test data is not producable. See #5.
20 | T | Gallery. Delete photo |  | Critical | Can't be verified | See #21
22 | T | Full screen photo view. |  | Critical | Can't be verified | Test data is not producable. See #5.
23 | T | Photo view. Delete photo |  | Critical | Can't be verified | Works for gallery but can't be verified on photo view. See #5
24 | T | Photo view. View bars |  | Critical | Can't be verified | Test data is not producable. See #5.
27 | T | Photo view. View description |  | Critical | Can't be verified | Test data is not producable. See #5.
28 | T | Photo view. Edit description |  | Critical | Can't be verified | Test data is not producable. See #5.
29 | T | Photo view. Swiping |  | Critical | Can't be verified | Test data is not producable. See #5.
10 | T | Galleries navigation |  | Critical | Done
32 | B | Gallery. Photo is selected when edit is off. | 1. Open server gallery 2. Click Edit and select a photo 3. Click OK. 4. Click photo Actual: Edit mode is off. Photo is selected. But should be opened instead | Major | New
33 | B | Settings. Photos in backgroun is clickable. | 1. Open server gallery 2. open Settings screen and click on the settings screen (for example on uploading folder) Actual: Photo whish was in bachgrounded gallery is opened | Major | New
34 | B | Gallery. Edit Mode. Camera button should not be presented |  | Major | New
6 | B | Login failed alert is ugly |  | Minor | New | Description could not be provided. See #1
12 | B | Galleries navigation shows empty content on quick swiping | 1. Open Main screen. 2. Swipe fast between server folders. Actual: Empty page is show for a second. | Minor | New
| Severity | Defenition
| Blocker | Blocks testing process or workflow
| Critical | All tasks must be impl in Phase 1.
| Major | Normal priority bugs
| Minor | Will be processed as minor issue, not focus on this now
| Status | Defenition
| Not implemented | Not implemented in the latest build 0.4.5
| Can't be verified | Task is blocked by issue or incomplete feature
| Incomplete | Some elements or f-ty is missing
| New | New bug
| Done | Completed
| Disappeared | F-ty or it's parts was presented earlier