## Estimate
B11:B157
PRELIMINARY PROJECT ESTIMATE | [6 empty] | #LA002 |  |  | E11:E157
LinkAvie |  |  |  | AS OF 20140402 | [5 empty] | H11:H157
I11:I157
PREPARED FOR:Thomas Luquet | [9 empty] | 10
PREPARED BY: <Mikhail Korovkin - TechLead>
REVIEWED BY: <Name - Position>
COMMITTABLE CONFIDENCE: |  |  | 99%
# | DESCRIPTION |  | OPTIMISTIC | MOST LIKELY | BUFFER | PESSIMISTIC | PERT | 99% | COMMENTS
1 | PRE-STUDY / PREPARING COMMITTABLE PLAN |  | 14 | 18 |  | 21.6 | 17.9333
S | Product vision development |  | 0 | 0 | 0% | 0 | 0 | 0 | Effort for creation of a brief vision statement: what business problem the product is going to solve, who will benefit from using the product etc.
S | Product requirements workshops |  |  |  |  | N/A | N/A | N/A
D | User interface prototyping workshops |  |  |  |  | N/A | N/A | N/A
D | User experience concept design |  |  |  |  | N/A | N/A | N/A
S | Product requirements specification and approval |  | 8 | 10 | 20% | 12 | 10 | 11.6
S | Drafting software architecture |  | 0 | 0 | 0% | 0 | 0 | 0
P | Project estimation and planning |  | 6 | 8 | 20% | 9.6 | 7.9333 | 9.3 | Activities aimed at preparing a committable estimate, schedule and Project Management Plan
M | Management and communication during pre-study |  |  |  |  | N/A | N/A | N/A
[6 empty] | N/A | N/A | N/A
2 | "ITERATION ZERO" |  | 8 | 12 |  | 14.4 | 11.7333
S | High-level architecture and system design |  | 0 | 0 | 0% | 0 | 0 | 0
T | Test strategy planning |  |  |  |  | N/A | N/A | N/A
| Graphics design |  |  |  |  | N/A | N/A | N/A
B | Development environment setup |  | 8 | 12 | 20% | 14.4 | 11.7333 | 14 | Make sure to include time required not only to set up developers' workstations, but also for setting up any development server(s) and CI environment(s).
T | Testing environment setup |  | 0 | 0 | 0% | 0 | 0 | 0
T | Staging environment setup |  | 0 | 0 | 0% | 0 | 0 | 0
| Project-specific trainings for the project team |  |  |  |  | N/A | N/A | N/A
[6 empty] | N/A | N/A | N/A
[6 empty] | N/A | N/A | N/A
3 | CONSTRUCTION | SIZE | 958.6 | 1378.8 |  | 1620.2125 | 1349.0021
| Dashboad new actions | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3 | News from my communities (new album shared) Invitation accept notifications (events, communities)
| User name "Welcome message" customizable from back-office | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8
| Add contacts | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3 | Full (Gmail, yahoo, hotmail, manual) / invitation process to become "Friend" + When you write an email address it put it as tag bellow the input field (like gmail), then you can add another email address in empty field again and so on.
| Add to group | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8
| End Friend a relation (Remove a friend) | XXS | 1.6 | 2.4 | 10% | 2.64 | 2.3067 | 2.6
| View groups (Multi-pages mgt) | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Add a group | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Search a group | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8
| Delete a group | XXS | 1.6 | 2.4 | 10% | 2.64 | 2.3067 | 2.6
| Modify a group | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8
| Rename a group | XXS | 1.6 | 2.4 | 10% | 2.64 | 2.3067 | 2.6
| My subscription promotional popup | XXS | 1.6 | 2.4 | 10% | 2.64 | 2.3067 | 2.6
| Offering and Pricelist integration via Back-office | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23
| My subscription Status (Service/Expiration date/Management) | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8
| My invoices | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8
| Subscription / Online payment / Online invoice | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23
| Settings: Friends Comments | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Uploads in background | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23 | Make uploads in background, so that if user is uploading many pictures, he can do other things in parallel
| Enhanced Middle-Footer Marketing page back-office creation | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23 | Enhance Middle-footer to create different Framed-in Marketing pages in the back-office and call them from the Middle-Footer configuration. Have the capability in Framed-in Page to create a button with a name and a link (ex: Try for Free LINKAVIE Enterprise)
| Tags management | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23 | Tags and SEARCH on tags (Wikipedia like) of contents based on tags + Tag management on Pictures, documents, videos (Vault), page, chapters, albums
| Video Vault | XL | 38.3 | 52.2 | 25.25% | 65.38 | 52.08 | 62.7 | Videos implementation, max video size accepted for upload 2GB, with sharing settings, (include item description edit) with view filtering + Add video block to Digital Album (Video from vault or youtube video with thumbnail with short description)
| Documents Vault | XL | 38.3 | 52.2 | 25.25% | 65.38 | 52.08 | 62.7 | Documents implementation, including item description edit, sharing settings, (seperated from Multimedia vault) with subfolders tags / Filter show per date or name + Add documents to Digital album document blocks
| Vault reorganization (custom view) + Vault views | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3 | Be able to move (draging with mouse to other position) a selection of pictures (resp videos) to have a new organization than the default one (Custom view) / Manage different views by Tags, date ascending, descending (default), name, customized
| Videos blocks integration into pages | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Documents block integration | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| 5 Additional themes for Digital albums => 8 same themes (3 from alpha 2 + 5 new ones) for Printable books | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| A Community manager is able to define/import its own templates themes for his community. Quick guideline to provide | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23
| Delete an album | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8
| Add/delete comments | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Text block enhancement | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23 | Smart integration text/picture + text/image links, other page links etc..
| Synchronize a Friend page/chapter or entire album | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23 | Friend to Friend page/chapter replication or entire album replication
| Share a page/chapter/album within Linkavie | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3 | Sharing settings management to integrate "allow share" and "Allow sync"
| Manage links between "My Life album" and "Personal albums" and differentiate from "other albums" type |  | Size? | Size? | Size? | N/A | N/A | N/A
| Create a printable Photo book (automatic) and save it to the Library | XL | 38.3 | 52.2 | 25.25% | 65.38 | 52.08 | 62.7
| Define/change shelf position | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8
| Edit a Photo book | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Share a Photobook | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Order a Printable Album | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23
| Create an event full process (Personal + Common events) | XL | 38.3 | 52.2 | 25.25% | 65.38 | 52.08 | 62.7 | including payment process for extending common event period, including event UI navigation, default event settings, user permissions per role (Owner, contributor, friend)
| Event settings feature | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3 | settings setup, extending a common event
| Contributors management: Adding/ending contributors | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Event storage management | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Event vault integration | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3 | with vault features per role, storage management etc..
| Event Digital album integration | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3 | with features per role, including adding comments.
| Share an event (Event owner) / Invitation process | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8
| Access an event (Vault, Album, photobook) after invitation | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8 | with the rigth user features set per role, add comments
| Generate/Modify Photo book (by owner only) integration within event | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Order Photo book (by owner only) integration within event | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8
| Synchronize an event | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8 | Re-integration into personal space (Vault, album, library, photobook), managing album and photobook broadcating control with newly sharing rights
| Extending a common event | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8
| Closing an event | XXS | 1.6 | 2.4 | 10% | 2.64 | 2.3067 | 2.6 | including automatic closing for a common event expiration, managing event expiration alerts
| Mobile event Back-office event code generation | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8
| Folder settings "Mobile event folder" | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8
| Event settings: Mobile event | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8
| API / Communication of site with Mobile App | L | 22.7 | 33.9 | 24.44% | 42.185 | 33.4142 | 40.6
| My communities page | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3 | create new community button, list communities, links to community pages under actions button - Navigation level
| Organization community license management, customer and payment back-office management | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Create a community full process | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3 | Trial or with license code, including community UI navigation, default community settings, user permissions per roles (Manager, contributor, album owner, member)
| Community account | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23 | Status, invoice with back-office orders/payment management
| Renewing / upgrading Community account | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8
| Public access to a community | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8 | via iframed link with parameters (Public community or user name/pwd, show/hide logo)
| Community settings | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Delete a community | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8 | Cleanup + email notifications
| Community contacts page | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23 | Show contacts with roles etc… + Invite button - Navigation level, Inviting method 1 (import users or manual emails), Inviting method 2 (Generate URL)
| Community contacts page | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8 | Search community member + Filter view
| Community contacts page | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8 | ending roles, changing role
| My Communities page | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3 | Change/end my role, transfer Manager role
| Community users rights management | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Community vault integration | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23 | with vault features per role, storage management etc..
| Community Digital album with Album level settings | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8
| Community Album level contact management | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23 | invite, end/change role
| Community Digital album integration | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23 | with features per role, including adding comments
| Share a community album | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8 | (community manager or album owner) / Invitation process, integrating on top community members.
| Synchronize a community album | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8 | or photo book into personal space with broadcating control depending of sharing rights
| Community Confidentiality / Sharing settings | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3 | Community owner or album owner can select contents and change the sharing settings for the selected items in regards to the members or contributors.
| Community Library | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23
| Generate/Modify Photo book (by owner only) integration within community | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Order Photo book (when shared by owner) integration within community | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Community Content moderation / Manage page updates moderation | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23
| Community Comments moderation | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Landing page SEARCH | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23 | Search of user or community according to authorizations setup by subscribers
| Landing page Request to setup a Relationship (auth required) | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8
| Landing page Access a Friend Life Album (auth required) | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8
| Landing page Request to become member of a community (auth required) | XS | 3.05 | 4.3 | 12.33% | 4.83 | 4.18 | 4.8
| Landing Page Direct access | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3 | to a Public Community Life Album or Public content of a community (No auth required)
| Landing Page Direct access | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3 | Direct access to a Private Community Life Album (Auth required)
| Back-office enhancement for B2C subscriptions | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23 | From user list: - edit expiration date - Edit user total storage capacity - Search/filter view feature (per keyword typed) - Orders management in Back-office
| Back-office enhancement for events | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23 | Event back-office management
| Back-office enhancement for Communities | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23 | Community back-office management
| Reports: registration month after month | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Reports: total storage month after month | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Reports: registration growth analysis (New users vs invited users) | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Reports: logins and visualize this "3D" report | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Reports: upload pictures per new user groups | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Reports: create page per new user groups | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Change update the Service packs definitions | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23 | duration / storage capacity / price
| Tracked registration links | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23 | Be able to generate different registration links (per partner for instance) and be able to track registrations and Business per specific registration links.
| Delete a user | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3 | properly deletes all contents, DB links to other users, events, communities, except if manager of a community
| Add/Delete a community | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23 | properly deletes all contents, DB, links to other users and manages emails notifications
| Edit any profile fields of community (service, expiration date, storage capacity etc...) or settings of a community | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3
| Adds management in back-office for free users | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23
| Incentive tool | L | 22.7 | 33.9 | 24.44% | 42.185 | 33.4142 | 40.6
| Storage capacity used | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23 | Total, average per user (split between photos, videos, musics, documents) and per community + Filter per user profiles (Free, paid users, per service pack).
| Split of service subscriptions per user types | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23 | (Free users, servic packs): Total amount or on a selected period
| List + email of free users | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3 | using the service since more than x months (x can be defined)
| Dashboards of renewals that should come on a coming period | S | 7.25 | 10.1 | 13.99% | 11.5125 | 9.8604 | 11.3 | to be defined (filter = Next month, next quarter), shows/filterautomatic and non automatic renewals. For users and Communities
| LINKAVIE https support after login | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23
| Documents & user passwords encryption | M | 13.3 | 20 | 17.62% | 23.525 | 19.4708 | 23
4 | STABILIZATION AND DELIVERY |  | 0 | 0 |  | 0 | 0
T | Regression testing |  |  |  |  | N/A | N/A | N/A | Includes regression testing efforts at the end of each sprint, including the release stabilization sprint
T | User interface testing |  |  |  |  | N/A | N/A | N/A
B | Release stabilization |  |  |  |  | N/A | N/A | N/A | This line includes efforts only for fixing a small amount of outstanding low-priority defects and "last minute" defects found during the final round(s) of regression testing. Effort for all other defect correction work must be included into Section 3.
I | Installation package preparation |  |  |  |  | N/A | N/A | N/A | Assumes manual assembly of the installation package, preparation of the installation instructions, and testing of the prepared package. In case when an automated installer is needed, remove this line item and estimate the installer as yet another feature in the "Construction" section.
I | Iteration demos |  |  |  |  | N/A | N/A | N/A
I | Deployment to staging environment |  |  |  |  | N/A | N/A | N/A
I | Deployment to production environment |  |  |  |  | N/A | N/A | N/A
I | Acceptance testing support |  |  |  |  | N/A | N/A | N/A
5 | MANAGEMENT AND COMMUNICATION |  | 0 | 0 |  | 0 | 0
S | Product requirements clarifications and updates |  |  |  |  | N/A | N/A | N/A | Include all efforts to be spent on requirements clarification, elaborating details, updating requirements specifications, and on requirements-related communications with the customer here
P | Iteration planning meetings |  |  |  |  | N/A | N/A | N/A
M | Iteration retrospective meetings |  |  |  |  | N/A | N/A | N/A
M | Daily progress & status meetings |  |  |  |  | N/A | N/A | N/A
M | Configuration management |  |  |  |  | N/A | N/A | N/A | Estimate effort required to carry out the standard CM activities (identification, control, status accounting and audits) at the level of formality appropriate for the project
M | Change management |  |  |  |  | N/A | N/A | N/A | Include efforts for change request analysis, impact analysis, estimation and communication with the customer related to change requests.
M | Project management and communication |  |  |  |  | N/A | N/A | N/A | Include all PM and Team Lead's efforts here except for management and communication efforts spent during the pre-study phase.
M | Project close-out |  |  |  |  | N/A | N/A | N/A | Efforts required to finalize the project, write the project close-out report, hold a project retrospective/lessons learned meeting etc.
| GRAND TOTAL |  | 980.6 | 1408.8 |  | 1656.2125 | 1378.6687 |  |  | 209.0515
14.4586
SUMMARY: |  |  |  |  | NOTE: |  |  |  |  | 1
Project Work Range |  |  | 981 - 1656 man-hours |  | This estimate is based on our understanding of the requirements at this time and is subject to change if something new is learned during the course of this project, in particular upon the completion of the Requirements, Analysis and Design activities. |  |  |  |  | 27.5
Expected Project Work (50% Confidence) |  |  | 1378,7 man-hours | [6 empty] | 19.2
Confidence in the Entire Range |  |  | 100,0% (-27,5σ .. +19,2σ)
90% Confidence Range |  |  | 1355 - 1402 man-hours
95% Confidence Range |  |  | 1350 - 1407 man-hours
99.9% Confidence Range |  |  | 1331 - 1426 man-hours
Project Duration |  |  | XX - YY business days
Programmers |  |  | TBD
QA |  |  | TBD
Project manager |  |  | TBD

## Efforts per Feature Size
ESTIMATED EFFORTS PER FEATURE SIZE: BOTTOM-UP APPROACH
INSTRUCTIONS
This worksheet assumes proxy-based estimation based on the T-Shirt Sizes technique and contains a boilerplate WBS for each feature size. You need to pick a "reference" feature for each size and fill out the corresponding WBS section with effort estimates in man-hours (calibrated historical data are preferred, if available). DO NOT round up these granular estimates to prevent "bloating" of the total figures, use of small fractions is OK here. Once you complete your entry for a specific size, subtotals for the minimum, maximum and most likely values for this feature size become available in the Summary section below. You can then pick a feature size in the in-cell drop-down next to a feature line item on the Estimate worksheet and have the Optimistic, Most Likely, Buffer and Pessimistic values populated automatically. Make sure to adjust the WBS to fit the project specifics and the established DONE-DONE criteria.
PIECE OF CAKE (XXS)
TASK | OPTIMISTIC | MOST LIKELY | BUFFER | PESSIMISTIC
Requirements analysis and clarification | 0.1 | 0.15 | 10% | 0.165 | S
Middle- and low-level technical design | 0.15 | 0.3 | 10% | 0.33 | D
Peer technical design review | 0.15 | 0.2 | 10% | 0.22 | D
Test case design | 0.15 | 0.2 | 10% | 0.22 | T
Test data creation | 0 | 0 | 0% | 0 | T
Development | 0.5 | 0.8 | 10% | 0.88 | B
Unit testing | 0 | 0 | 0% | 0 | B
Peer code review | 0 | 0 | 0% | 0 | B
Testing by developer | 0.15 | 0.2 | 10% | 0.22 | B
Functional testing | 0.15 | 0.2 | 10% | 0.22 | T
Defect correction | 0.15 | 0.2 | 10% | 0.22 | B
Defect verification | 0.1 | 0.15 | 10% | 0.165 | T
TOTAL | 1.6 | 2.4 | 10% | 2.64
EASY (XS)
TASK | OPTIMISTIC | MOST LIKELY | BUFFER | PESSIMISTIC
Requirements analysis and clarification | 0.2 | 0.3 | 10% | 0.33 | S
Middle- and low-level technical design | 0.2 | 0.3 | 10% | 0.33 | D
Peer technical design review | 0.2 | 0.3 | 10% | 0.33 | D
Test case design | 0.2 | 0.3 | 10% | 0.33 | T
Test data creation | 0 | 0 | 0% | 0 | T
Development | 1.5 | 2 | 15% | 2.3 | B
Unit testing | 0 | 0 | 0% | 0 | B
Peer code review | 0 | 0 | 0% | 0 | B
Testing by developer | 0.2 | 0.3 | 10% | 0.33 | B
Functional testing | 0.2 | 0.3 | 10% | 0.33 | T
Defect correction | 0.2 | 0.3 | 10% | 0.33 | B
Defect verification | 0.15 | 0.2 | 10% | 0.22 | T
TOTAL | 3.05 | 4.3 | 12.33% | 4.83
AVERAGE (S)
TASK | OPTIMISTIC | MOST LIKELY | BUFFER | PESSIMISTIC
Requirements analysis and clarification | 0.25 | 0.35 | 15% | 0.4025 | S
Middle- and low-level technical design | 0.5 | 0.7 | 15% | 0.805 | D
Peer technical design review | 0.3 | 0.35 | 10% | 0.385 | D
Test case design | 0.5 | 0.7 | 10% | 0.77 | T
Test data creation | 0 | 0 | 0% | 0 | T
Development | 4 | 5 | 15% | 5.75 | B
Unit testing | 0 | 0 | 0% | 0 | B
Peer code review | 0 | 0 | 0% | 0 | B
Testing by developer | 0.5 | 0.7 | 10% | 0.77 | B
Functional testing | 0.5 | 1 | 15% | 1.15 | T
Defect correction | 0.5 | 1 | 15% | 1.15 | B
Defect verification | 0.2 | 0.3 | 10% | 0.33 | T
TOTAL | 7.25 | 10.1 | 13.99% | 11.5125
HARD (M)
TASK | OPTIMISTIC | MOST LIKELY | BUFFER | PESSIMISTIC
Requirements analysis and clarification | 0.5 | 0.8 | 15% | 0.92 | S
Middle- and low-level technical design | 0.5 | 1 | 15% | 1.15 | D
Peer technical design review | 0.4 | 0.5 | 15% | 0.575 | D
Test case design | 1 | 1.5 | 10% | 1.65 | T
Test data creation | 0 | 0 | 0% | 0 | T
Development | 8 | 12 | 20% | 14.4 | B
Unit testing | 0 | 0 | 0% | 0 | B
Peer code review | 0 | 0 | 0% | 0 | B
Testing by developer | 1 | 1.5 | 15% | 1.725 | B
Functional testing | 0.7 | 1 | 15% | 1.15 | T
Defect correction | 0.8 | 1.2 | 15% | 1.38 | B
Defect verification | 0.4 | 0.5 | 15% | 0.575 | T
TOTAL | 13.3 | 20 | 17.62% | 23.525
VERY DIFFICULT (L)
TASK | OPTIMISTIC | MOST LIKELY | BUFFER | PESSIMISTIC
Requirements analysis and clarification | 0.8 | 1 | 15% | 1.15 | S
Middle- and low-level technical design | 0.5 | 1.2 | 15% | 1.38 | D
Peer technical design review | 0.5 | 0.7 | 15% | 0.805 | D
Test case design | 1.5 | 2 | 15% | 2.3 | T
Test data creation | 0 | 0 | 0% | 0 | T
Development | 14 | 20 | 30% | 26 | B
Unit testing | 0 | 0 | 0% | 0 | B
Peer code review | 0 | 0 | 0% | 0 | B
Testing by developer | 2 | 3 | 15% | 3.45 | B
Functional testing | 1.5 | 3 | 15% | 3.45 | T
Defect correction | 1.2 | 2 | 25% | 2.5 | B
Defect verification | 0.7 | 1 | 15% | 1.15 | T
TOTAL | 22.7 | 33.9 | 24.44% | 42.185
EXTREME, BUT KNOWN (XL)
TASK | OPTIMISTIC | MOST LIKELY | BUFFER | PESSIMISTIC
Requirements analysis and clarification | 1.5 | 2 | 15% | 2.3 | S
Middle- and low-level technical design | 1 | 2 | 20% | 2.4 | D
Peer technical design review | 0.8 | 1.2 | 15% | 1.38 | D
Test case design | 2 | 3 | 15% | 3.45 | T
Test data creation | 0 | 0 | 0% | 0 | T
Development | 24 | 30 | 30% | 39 | B
Unit testing | 0 | 0 | 0% | 0 | B
Peer code review | 0 | 0 | 0% | 0 | B
Testing by developer | 3 | 4 | 15% | 4.6 | B
Functional testing | 2 | 3.5 | 15% | 4.025 | T
Defect correction | 3 | 5 | 30% | 6.5 | B
Defect verification | 1 | 1.5 | 15% | 1.725 | T
TOTAL | 38.3 | 52.2 | 25.25% | 65.38
EXTREME AND UNKNOWN (XXL)
TASK | OPTIMISTIC | MOST LIKELY | BUFFER | PESSIMISTIC
Requirements analysis and clarification |  |  |  | N/A | S
Middle- and low-level technical design |  |  |  | N/A | D
Peer technical design review |  |  |  | N/A | D
Test case design |  |  |  | N/A | T
Test data creation |  |  |  | N/A | T
Development |  |  |  | N/A | B
Unit testing |  |  |  | N/A | B
Peer code review |  |  |  | N/A | B
Testing by developer |  |  |  | N/A | B
Functional testing |  |  |  | N/A | T
Defect correction |  |  |  | N/A | B
Defect verification |  |  |  | N/A | T
TOTAL | 0 | 0 | N/A | 0
XXS_CellRefs | $B$8:$B$19 | $C$8:$C$19 |  | $E$8:$E$19 | $F$8:$F$19
XXS_Requirements | 0.1 | 0.15 |  | 0.165 | 0.14417
XXS_Design | 0.3 | 0.5 |  | 0.55 | 0.475
XXS_Construction | 0.8 | 1.2 |  | 1.32 | 1.1533
XXS_Test | 0.4 | 0.55 |  | 0.605 | 0.53417
XS_CellRefs | $B$25:$B$36 | $C$25:$C$36 |  | $E$25:$E$36 | $F$25:$F$36
XS_Requirements | 0.2 | 0.3 |  | 0.33 | 0.28833
XS_Design | 0.4 | 0.6 |  | 0.66 | 0.57667
XS_Construction | 1.9 | 2.6 |  | 2.96 | 2.5433
XS_Test | 0.55 | 0.8 |  | 0.88 | 0.77167
S_CellRefs | $B$41:$B$52 | $C$41:$C$52 |  | $E$41:$E$52 | $F$41:$F$52
S_Requirements | 0.25 | 0.35 |  | 0.4025 | 0.34208
S_Design | 0.8 | 1.05 |  | 1.19 | 1.0317
S_Construction | 5 | 6.7 |  | 7.67 | 6.5783
S_Test | 1.2 | 2 |  | 2.25 | 1.9083
M_CellRefs | $B$57:$B$68 | $C$57:$C$68 |  | $E$57:$E$68 | $F$57:$F$68
M_Requirements | 0.5 | 0.8 |  | 0.92 | 0.77
M_Design | 0.9 | 1.5 |  | 1.725 | 1.4375
M_Construction | 9.8 | 14.7 |  | 17.505 | 14.3508
M_Test | 2.1 | 3 |  | 3.375 | 2.9125
L_CellRefs | $B$73:$B$84 | $C$73:$C$84 |  | $E$73:$E$84 | $F$73:$F$84
L_Requirements | 0.8 | 1 |  | 1.15 | 0.99167
L_Design | 1 | 1.9 |  | 2.185 | 1.7975
L_Construction | 17.2 | 25 |  | 31.95 | 24.8583
L_Test | 3.7 | 6 |  | 6.9 | 5.7667
XL_CellRefs | $B$89:$B$100 | $C$89:$C$100 |  | $E$89:$E$100 | $F$89:$F$100
XL_Requirements | 1.5 | 2 |  | 2.3 | 1.9667
XL_Design | 1.8 | 3.2 |  | 3.78 | 3.0633
XL_Construction | 30 | 39 |  | 50.1 | 39.35
XL_Test | 5 | 8 |  | 9.2 | 7.7
XXL_CellRefs | $B$105:$B$116 | $C$105:$C$116 |  | $E$105:$E$116 | $F$105:$F$116
XXL_Requirements | 0 | 0 |  | 0 | 0
XXL_Design | 0 | 0 |  | 0 | 0
XXL_Construction | 0 | 0 |  | 0 | 0
XXL_Test | 0 | 0 |  | 0 | 0
| 4.18 | 9.8604 | 19.4708 | 33.4142 | 52.08 | 2.3067 | 0
ACTIVITY EFFORT BREAKDOWN | XXS | XS | S | M | L | XL | XXL
Specify | 6.25% | 6.898% | 3.469% | 3.955% | 2.968% | 3.776% | N/A
Design | 20.59% | 13.8% | 10.46% | 7.383% | 5.379% | 5.882% | N/A
Build | 60.85% | 60.85% | 66.71% | 73.7% | 74.39% | 75.56% | N/A
Test | 18.46% | 18.46% | 19.35% | 14.96% | 17.26% | 14.78% | N/A

## Checklist
THE CHECKLIST
ITEM | [8 empty] | YES/NO | PLEASE PROVIDE COMMENTS FOR EVERY "NO" AND "N/A"
1 | The estimate objectives are known and clear to the estimation team. | [7 empty] | Yes
2 | All the members of the estimation team have sufficient understanding of the project scope to meet the set forth estimation objectives. All open questions are specified as reasonable assumptions and/or accounted for as potential risks. | [7 empty] | N/A | Not all details, but general idea
3 | Operating systems, technology and programming language(s) have been clearly defined. | [7 empty] | Yes
4 | A summary or list of significant deliverables (software and documentation) produced by the project has been defined. | [7 empty] | Yes
5 | The estimation process was free from pressure that would bias the results. | [7 empty] | Yes
6 | The estimators followed a structured process to estimate the software product. | [7 empty] | N/A | First try
7 | Chosen estimation techniques are applicable to the current stage of the project. | [7 empty] | N/A | Some fields are non needed
8 | Techniques based on counting and computation were given priority over expert judgment where possible. | [7 empty] | Yes
9 | The estimators followed a structured process to estimate and describe the extent of reuse, primarily by adopting 3rd party libraries. The measures of reuse distinguish between code that will be modified and code that will be integrated as-is. | [7 empty] | Yes
10 | People who are going to do the work have been involved in creating the estimate (provided this was at all possible). | [7 empty] | No | They already has a lot of tasks
11 | Only the inputs to the estimate were negotiated, but not the outputs or the estimation process. | [7 empty] | Yes
12 | The estimation team considered data from similar past projects , and adjustments were made when required to reflect the specifics of the software product being estimated. | [7 empty] | Yes
13 | The estimate is double-checked for full traceability to the scope of the project. | [7 empty] | No | First estimate example in new format. Should be double-checked on each stage.
14 | The values in the "Optimistic" column do really represent the best "sunny day" scenario. The values in the "Most Likely" column represent the realistic scenario. The buffer percentage is used to calculate allowance for mitigating perceived risks. | [7 empty] | Yes
15 | The estimate is double-checked for inclusion of all necessary software development activities prescribed by the applicable SDLC, not just coding and testing. | [7 empty] | Yes
16 | Technical supervision / review efforts have been added to the estimate of every task where they are required and can be "sold" to the customer. | [7 empty] | Yes
17 | Efforts such as QA, graphics design etc. have been estimated by experts in the respective functions. | [7 empty] | No | Too bad
18 | I requested usability requirements and standards from the customer and added corresponding usability analysis, study and testing effort to the estimate. The effort was estimated by a Company's usability expert. | [7 empty] | Yes
19 | Project management efforts have been validated against the expected project duration. | [7 empty] | No
20 | The estimate includes all involved hardware and software licensing costs or stares that such costs are not included.
21 | The estimate includes all involved travel costs or states that such costs are not included.
22 | The estimate includes efforts for project domain-specific trainings.
23 | The estimate does NOT include efforts for technology trainings.
24 | The estimate's accuracy is achievable given the current stage of the project according to "The Cone of Uncertainty".
25 | The estimate is expressed as a range with precision that matches its accuracy.
26 | The productivity factor underlying the estimate is comparable to productivity actually experienced on past projects of similar sizes. If past productivity is unknown, an average developer's productivity is assumed.
27 | The estimate includes a nonzero allowance for the impact that project risks will have on effort and schedule.
28 | The estimated duration in months is at least
29 | All assumptions made in support of the estimate are identified, documented, and explained.
30 | The estimate has been reviewed by an independent expert who did not participate in creating the estimate.
31 | No commitments are made until the estimate accuracy is sufficiently narrow (± 20%).
32 | The "Revision History" worksheet has been removed unless it contains the revision history of the estimate template itself.
33 | The actual effort breakdown percentage corresponds to the expected one for given application size and type.
| 32 | 139 | Estimate!D32:D139 | Estimate!I32:I139
| Estimate!$B11:$B157 |  | Estimate!$I11:$I157 |  |  | Estimate!$D11:$D157
| 0 | 7.9333 | 7.9333 |  | Plan
| 53.9413 | 10 | 63.9413 |  | Specify
| 116.3417 | 0 | 116.3417 |  | Design
| 953.0883 | 11.7333 | 964.8217 |  | Build
| 225.6308 | 0 | 225.6308 |  | Test
| 0 | 0 | 0 |  | Implement
| 0 | 0 | 0 |  | Management
| ACTUAL EFFORT BREAKDOWN |  |  | MAN-HRS |  | ACTUAL % | EXPECTED % | DIFF
| Plan |  |  |  | 7.9333 | 0.5754% | 1.5% | -0.9246%
| Specify |  |  |  | 63.9413 | 4.638% | 12.5% | -7.862%
| Design |  |  |  | 116.3417 | 8.439% | 15.5% | -7.061%
| Build |  |  |  | 964.8217 | 69.98% | 24.5% | 45.48%
| Test |  |  |  | 225.6308 | 16.37% | 15% | 1.366%
| Implement |  |  |  | 0 | 0% | 12% | -12%
| Management |  |  |  | 0 | 0% | 15% | -15%
PROJECT PARAMETERS ENTRY
Choose the best matching project type:
Ballpark project size, KSLOC:
Adjusting for:
2.0∗ ∛𝑆𝑡𝑎𝑓𝑓𝑀𝑜𝑛𝑡ℎ𝑠

## Lookups (hidden)
L | L_Min | L_Likely | L_Buffer | L_Max
M | M_Min | M_Likely | M_Buffer | M_Max
S | S_Min | S_Likely | S_Buffer | S_Max | S | P | Yes | 90%
XL | XL_Min | XL_Likely | XL_Buffer | XL_Max | D | S | No | 99%
XS | XS_Min | XS_Likely | XS_Buffer | XS_Max | B | D | N/A
XXL | XXL_Min | XXL_Likely | XXL_Buffer | XXL_Max | T | B
XXS | XXS_Min | XXS_Likely | XXS_Buffer | XXS_Max |  | T
I
| R | D | C | T | M | M
1 | 0.04 | 0.1 | 0.61 | 0.16 | 0.09 |  | Test data creation
5 | 0.04 | 0.124 | 0.528 | 0.199 | 0.109
25 | 0.04 | 0.14 | 0.49 | 0.23 | 0.1
75 | 0.055 | 0.145 | 0.465 | 0.23 | 0.105
125 | 0.07 | 0.15 | 0.44 | 0.23 | 0.11
300 | 0.075 | 0.15 | 0.395 | 0.26 | 0.12
500 | 0.08 | 0.15 | 0.35 | 0.29 | 0.13
| R | D | C | T | M
Business Systems | -0.03 | -0.07 | 0.05 | -0.07 | 0.03
Device Drivers | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Embedded Systems | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Engineering Systems | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Internal Intranet Systems | -0.03 | -0.07 | 0.05 | -0.07 | 0.03
Public Internet Systems | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Scientific Systems | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Shrink-Wrap | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Systems Software | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Telecommunications | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Advanced multi-site surveys application (MLR) | 300 | Internal Intranet Systems
Automated document archival solution (LTA) | 125 | Business Systems
Complex SharePoint-based public CMS solution (MTT) | 125 | Public Internet Systems
Highly customizable BI solution with interactive GUI (ACE) | 500 | Business Systems
Interactive iPad brochures for automotive industry (Subaru) | 25 | Shrink-Wrap
Racing event support website (WMRT) | 25 | Public Internet Systems
Simple data/format conversion solution (FSR) | 25 | Business Systems
Sophisticated data conversion/mapping solution (O2O) | 75 | Business Systems
Sophisticated enterprise content management platform (PLD) | 500 | Business Systems
Trivia game rich Internet application (VRG) | 5 | Public Internet Systems
Trivia game server-side application (VRG) | 5 | Public Internet Systems
Web portal integrated with internal business system (PWP) | 25 | Public Internet Systems
Add new project size and classification entries above this line