## Estimate
PRELIMINARY PROJECT ESTIMATE |  | #0159-001-001-EST
Fashion Website |  | 24-JUN-2014
PREPARED FOR:
PREPARED BY:
REVIEWED BY:
# | DESCRIPTION | OPTIMISTIC ESTIMATE, HRS | PESSIMISTIC ESTIMATE, HRS
1 | PRE-STUDY / PREPARING COMMITTABLE PLAN | 0 | 0
Product vision development
Product requirements workshops
User experience concept design
Product requirements specification and approval
Project estimation and planning
Management and communication during pre-study
2 | "ITERATION ZERO" | 20 | 48
| High-level architecture and system design | 8 | 24
Test strategy planning
Graphics design
| Development environment setup/ server setup, install magento | 4 | 8
| Testing environment setup | 4 | 8
| Staging environment setup | 4 | 8
3 | CONSTRUCTION | 210 | 427
| Develop new theme according to http://www.thunderlily.com | 60 | 150 | depends on ui complexity
| Post sketches page with admin part | 24 | 48 | please describe admin actions
| Produce My Designs page with slider and custom info page | 12 | 16
| Explore sketches with commenting, ajax loading etc | 14 | 20
| Add WordPress extension and style the blog | 16 | 36
| Tutorial page based on blog tags | 4 | 5
| Custom Dressmakers extension (admin manage, frontend search) | 22 | 36
| Designers extension (menu links, admin manage, frontend view, shop designer pages) | 40 | 80
| Custom Made Clothes page with girl preview |  |  | need more info about this part
| Category extra logic | 6 | 12
| Blocks view tuning | 12 | 24
| Adding site content |  |  | depends on content size
4 | STABILIZATION AND DELIVERY | 0 | 0
Regression testing
User interface testing
Release stabilization
Deployment to staging environment
Deployment to production environment
Acceptance testing support
5 | MANAGEMENT AND COMMUNICATION | 0 | 0
Product requirements clarifications and updates
Iteration planning meetings
Iteration retrospective meetings
Daily progress & status meetings
Change management
Project management and communication
| GRAND TOTAL | 230 | 475

## Lookups (hidden)
L | L_Min | L_Likely | L_Buffer | L_Max
M | M_Min | M_Likely | M_Buffer | M_Max
S | S_Min | S_Likely | S_Buffer | S_Max | S | P | Yes | 90%
XL | XL_Min | XL_Likely | XL_Buffer | XL_Max | D | S | No | 99%
XS | XS_Min | XS_Likely | XS_Buffer | XS_Max | B | D | N/A
XXL | XXL_Min | XXL_Likely | XXL_Buffer | XXL_Max | T | B
XXS | XXS_Min | XXS_Likely | XXS_Buffer | XXS_Max |  | T
I
| R | D | C | T | M | M
1 | 0.04 | 0.1 | 0.61 | 0.16 | 0.09 |  | Test data creation
5 | 0.04 | 0.124 | 0.528 | 0.199 | 0.109
25 | 0.04 | 0.14 | 0.49 | 0.23 | 0.1
75 | 0.055 | 0.145 | 0.465 | 0.23 | 0.105
125 | 0.07 | 0.15 | 0.44 | 0.23 | 0.11
300 | 0.075 | 0.15 | 0.395 | 0.26 | 0.12
500 | 0.08 | 0.15 | 0.35 | 0.29 | 0.13
| R | D | C | T | M
Business Systems | -0.03 | -0.07 | 0.05 | -0.07 | 0.03
Device Drivers | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Embedded Systems | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Engineering Systems | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Internal Intranet Systems | -0.03 | -0.07 | 0.05 | -0.07 | 0.03
Public Internet Systems | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Scientific Systems | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Shrink-Wrap | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Systems Software | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Telecommunications | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Advanced multi-site surveys application (MLR) | 300 | Internal Intranet Systems
Automated document archival solution (LTA) | 125 | Business Systems
Complex SharePoint-based public CMS solution (MTT) | 125 | Public Internet Systems
Highly customizable BI solution with interactive GUI (ACE) | 500 | Business Systems
Interactive iPad brochures for automotive industry (Subaru) | 25 | Shrink-Wrap
Racing event support website (WMRT) | 25 | Public Internet Systems
Simple data/format conversion solution (FSR) | 25 | Business Systems
Sophisticated data conversion/mapping solution (O2O) | 75 | Business Systems
Sophisticated enterprise content management platform (PLD) | 500 | Business Systems
Trivia game rich Internet application (VRG) | 5 | Public Internet Systems
Trivia game server-side application (VRG) | 5 | Public Internet Systems
Web portal integrated with internal business system (PWP) | 25 | Public Internet Systems
Add new project size and classification entries above this line