## Estimate
PRELIMINARY PROJECT ESTIMATE |  | #0162-001-EST
|  | 25-JUN-2014 |  | НЕ ЗАБЫТЬ УДАЛИТЬ ЯЧЕЙКИ ВЫДЕЛЕННЫЕ ЖЕЛТЫМ ЦВЕТОМ!!!!
PREPARED FOR:
PREPARED BY: Anna Ieremenko - Project Manager
REVIEWED BY: Anatoly Lenshin - Program Director
|  | Provided by Developes |  | BUFFER, HRS |  | TO CLIENT
# | DESCRIPTION | OPTIMISTIC ESTIMATE, HRS | PESSIMISTIC ESTIMATE, HRS | FOR OPTIMISTIC, HRS | FOR PESSIMISTIC, HRS | OPTIMISTIC ESTIMATE, HRS | PESSIMISTIC ESTIMATE, HRS
1 | PRE-STUDY / PREPARING COMMITTABLE PLAN | 6 | 10 | 0 | 0 | 6 | 10
| Product vision / specification development | 6 | 10 |  |  | 6 | 10
2 | "ITERATION ZERO" | 3 | 6 | 0 | 0 | 3 | 6
| Test strategy planning | 1 | 2 |  |  | 1 | 2
| Development environment setup | 2 | 4 |  |  | 2 | 4
3 | CONSTRUCTION | 98 | 152 | 3 | 12 | 24 | 56
| 1) Install and configure new magento | 1 | 2 | 0 | 0 | 1 | 2
| 2) Configure multistore | 1 | 2 | 0 | 0 | 1 | 2
| 3) Install and configure theme bought by client | 4 | 6 | 1 | 6 | 5 | 12
| 4) Customize theme | 8 | 24 | 2 | 6 | 10 | 30
| 5) Create cms pages and static blocks | 8 | 12 | 0 | 0 | 8 | 12
| 6) Install and configure additional modules | 14 | 26 | 1 | 1 | 15 | 27
| 7) Configure tax zones, tax rules | 1 | 2 | 1 | 1 | 2 | 3
| 8) Configure user groups | 1 | 2 | 1 | 1 | 2 | 3
| 9) Add test data | 5 | 6 | 1 | 1 | 6 | 7
| 10) Create scripts for migration data | 30 | 40 | 0 | 20 | 30 | 60
| 11) Interaction with ALDOC | 25 | 30 | 0 | 10 | 25 | 40
4 | STABILIZATION AND DELIVERY | 44 | 68 | 0 | 0 | 44 | 68
| Functional testing | 24 | 40 |  |  | 24 | 40
| Release stabilization | 16 | 20 |  |  | 16 | 20
| Delivery package preparing | 4 | 8 |  |  | 4 | 8
5 | MANAGEMENT AND COMMUNICATION | 38 | 56 | 4 | 8 | 42 | 64
| Product requirements clarifications and updates | 12 | 16 |  |  | 12 | 16
| Progress & status meetings | 8 | 12 |  |  | 8 | 12
| Change management | 8 | 12 | 4 | 8 | 12 | 20
| Project management and communication | 8 | 12 |  |  | 8 | 12
| Project close-out | 2 | 4 |  |  | 2 | 4
| GRAND TOTAL | 189 | 292 | 11 | 54 | 200 | 346

## Lookups (hidden)
L | L_Min | L_Likely | L_Buffer | L_Max
M | M_Min | M_Likely | M_Buffer | M_Max
S | S_Min | S_Likely | S_Buffer | S_Max | S | P | Yes | 90%
XL | XL_Min | XL_Likely | XL_Buffer | XL_Max | D | S | No | 99%
XS | XS_Min | XS_Likely | XS_Buffer | XS_Max | B | D | N/A
XXL | XXL_Min | XXL_Likely | XXL_Buffer | XXL_Max | T | B
XXS | XXS_Min | XXS_Likely | XXS_Buffer | XXS_Max |  | T
I
| R | D | C | T | M | M
1 | 0.04 | 0.1 | 0.61 | 0.16 | 0.09 |  | Test data creation
5 | 0.04 | 0.124 | 0.528 | 0.199 | 0.109
25 | 0.04 | 0.14 | 0.49 | 0.23 | 0.1
75 | 0.055 | 0.145 | 0.465 | 0.23 | 0.105
125 | 0.07 | 0.15 | 0.44 | 0.23 | 0.11
300 | 0.075 | 0.15 | 0.395 | 0.26 | 0.12
500 | 0.08 | 0.15 | 0.35 | 0.29 | 0.13
| R | D | C | T | M
Business Systems | -0.03 | -0.07 | 0.05 | -0.07 | 0.03
Device Drivers | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Embedded Systems | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Engineering Systems | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Internal Intranet Systems | -0.03 | -0.07 | 0.05 | -0.07 | 0.03
Public Internet Systems | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Scientific Systems | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Shrink-Wrap | -0.2 | -0.05 | 0.02 | 0.09 | -0.15
Systems Software | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Telecommunications | 0.2 | 0.1 | -0.1 | 0.06 | 0.03
Advanced multi-site surveys application (MLR) | 300 | Internal Intranet Systems
Automated document archival solution (LTA) | 125 | Business Systems
Complex SharePoint-based public CMS solution (MTT) | 125 | Public Internet Systems
Highly customizable BI solution with interactive GUI (ACE) | 500 | Business Systems
Interactive iPad brochures for automotive industry (Subaru) | 25 | Shrink-Wrap
Racing event support website (WMRT) | 25 | Public Internet Systems
Simple data/format conversion solution (FSR) | 25 | Business Systems
Sophisticated data conversion/mapping solution (O2O) | 75 | Business Systems
Sophisticated enterprise content management platform (PLD) | 500 | Business Systems
Trivia game rich Internet application (VRG) | 5 | Public Internet Systems
Trivia game server-side application (VRG) | 5 | Public Internet Systems
Web portal integrated with internal business system (PWP) | 25 | Public Internet Systems
Add new project size and classification entries above this line